## To Do
Status | What | Who | DAYS | Priority (A/B/C/D) | Additional notes/details
Done | Case Comparer/Input List/SAM Spreadsheet/Parametrics | Steve/Aron | 3 | a
Done | integration with SAM user registration service | Aron/Rob | 2 | a |  | 39 | A-list
Done | Help system UI and content | Aron/Paul | 8 | a
Done | integration of report generator | Aron/Paul | 3 | a
Done | Scripting (LK) for general replacement of SamUL | Aron/Steve | 4 | a
Done | Solar prospector (download WF) linkage | Janine | 4 | a
Done | Option to not save hourly results | Aron | 0.5 | a
Done | General usability, including saving views in outputs, graphs | Everyone | 5 | a
Done | Testing!!! | Everyone | 5 | a
Done | Autographs and metrics tables for each technology | Janine/Steve | 3 | a
Done | Update wxPDFDocument library in WEX to version 0.9.4 | Aron | 0 | a
Done | Expand keyboard shortcuts | Janine | 0.5 | a
Done | Check shading support in pvwatts v5 | Janine | 1 | a
Done | Update defaults for all cases | ? |  | a
Done | Proxy support in SAMnt via proxy.txt | Aron | 0 | a
Done | csp generic solar | Tom | 2 | b
Done | Excel exchange for base case | Aron | 1.5 | b
Done | update all report templates | Paul | 5 | b | detailed pv report, basic for all other techs
Done | OpenEI utility rate database linkage | Aron/Steve | 5 | b
Done | Parametrics UI | Aron/Steve | 3 | b
Done | P50/P90 UI | Aron | 1 | b
Done | Monte Carlo/LHS (statisical) UI | Aron | 2 | b
Done | Macro system UI | Janine | 1 | b
Done | Integration of 3D shade calculator | Janine/Aron/Steve | 3 | b
Done | PV self-shading testing | Janine | 1 | b
Done | Re-arrange self-shading inputs in UI with system design? Sizing check? Check inputs for usability in SDK | Janine |  | b
Done | building load estimator impl in C++ and integration | Nate/Sara | 5 | b
Done | Fixes + ui tweaks to tech/market selection dialog | Aron | 0.5 | b
Done | Change shading factors to shading losses (%) | Janine |  | b
Done | Save DView timeseries state between simulations - i.e. restore checked values and graph axes | Aron |  | b
Done | Check SunEye Obstructions and both Solar Pathfinder file imports | Janine |  | b
Done | Simulation status and warnings dialog box | Aron | 2 | b
Done | Weather file settings dialog to set search path and download folder, rescan library, updates to UI | Aron |  | b
Done | HCPV user interface | Tom |  | c
Done | Molten salt power tower | Steve | 8 | b |  | 32 | B-list
Done | dish stirling | Tom |  | c
Done | SolarPILOT integration | Mike/Aron | 3 | b
Done | finish up send-to-excel with equations | Paul | 2 | b
Done | List of alpha feedback from Nate |  |  | b
Done | biomass power | Tom |  | c
Done | Wind barriers database linkage | Janine |  | c
Done | Parallelized simulation engine | Aron |  | c
Done | Access to about dialog/release notes/help - perhaps on welcome/startup page | Aron |  | c
Done | Restore "sun-orb" icon? Or keep "flat" metro look & feel | Aron |  | c
Done | Make sure we don't use WX HTTP functions - always use libcurl based wxSimpleCurl class |  |  | c
Done | Loss diagrams renderer updates and update for tech | Steve |  | c
Done | Fix zenith angle algorithm not to give junk values at night | Janine |  | c
Done | Check geothermal financing (lifetime etc) | Steve |  | c
Done | Proxy support fixing, potentially autodetection on Windows? |  |  | c
Done | Mac forms |  |  | c
Done | Defaults manager for updating default values in various configurations | Aron |  | c
Done | Direct steam power tower | Steve | 4 | c
Done | direct steam linear fresnel | Tom | 4 | c
Done | molten salt linear fresnel | Tom | 2 | c
Done | Re-export libraries from old SAM | Janine |  | c
Done | Fix output variable group names in SSC: Flat Plate, PVWatts, Wind, CSP Trough & Towers, Res, Comm | Janine
Done | Janine has to fix what Aron broke in the Macros | Janine
Done | Janine can sort TODO list | Janine
Done | Tower fixes - Steve & Mike | Steve/Mike
Done | Steam tower | Ty/Steve
Done | Molten salt linear fresnel - match with script from Ty | Steve
Done | Clean up the multiple load metrics reported to UI |  |  | c
Done | Wind - cost and scaling model | Tom
Done | Review default values, financial, cost #s for PV res/com/util | Everyone
Not done | Documentation updates from Paul | Paul
Done | Progress updates for solarpilot - Aron | Aron
Done | Add performance adjustment factors to wind model | Janine/Aron
Done | Possible registration issues
Done | Fix issue with InnoSetup uninstall win32 and x64 - windows 7 and window 8 | Steve |  |  | beta feedback
Done | UI text to explain URDB utility name aliasing issue (e.g., PG&E appears in list but without rates) | Paul |  |  | beta feedback
Done | Add time stamp column to time series data exported from data tables to Excel/CSV, also from time series data viewer if possible | Aron |  |  | beta feedback
Done | Weather file summary statistics on climate pages (total DNI, GHI, DHI in kWh/m2 and/or kWh/m2/day, average dry-bulb temperature, average wind speed) | Aron calculations, Paul UI |  |  | beta feedback
Done | Tool for populating ranges of parametric input variable values | Aron/Steve |  |  | beta feedback
Done | Investigate SWH model without electric load pages | Aron
Done | HCPV model: add option for irradiance table to be DNI based rather than cell POA based | Aron
POUT | Better weather file reader error reporting for EPW files from IWEC that have zeros for dew-point temperatures | Aron |  |  | beta feedback
Done | Registration pop-up window to explain what data NREL is collecting and why, with option to exit without registering | Aron |  |  | beta feedback
Done | Continue debugging time series data viewer |  |  |  | beta feedback
POUT | Text bigger than buttons when Windows display settings to more than 100% |  |  |  | beta feedback
Done | Single owner send to excel dscr=0 divide by zero issue | Paul |  |  | beta feedback
Done | Issue entering values on computers with language setting other than U.S. English | Aron |  |  | beta feedback
Done | SHIFT issue with TMY2 weather files causes CSP models to crash | Aron |  |  | beta feedback
Done | Startup issues for computers with right-to-left reading order | Aron |  |  | beta feedback, possible fix with WxWidgets update
Done | direct steam tower: receiver height calculated value is zero |  |  |  | H_rec and rec_height variables in UI, H_rec in ssc
Done | biopower: feedstock download buttons do not work | Aron
Done | geothermal: Lookup temp and depth button does not work | Aron
Done | SDK build | Steve
Done | CEC Inverter updates | Steve
Done | PBNS update for dispatch factors | Steve
Future | Move all CSP constants from ui to respective compute modules | Steve
Done | Fix issue with parametric grid editor read only display of monthly and hourly outputs.
Pre-release | Check the reports | Everyone
Pre-release | Check the macros | Everyone
Pre-release | Check all results, and summarize for release notes | Everyone
Pre-release | Check all default values | Everyone
Done | Vote against that horrible marigold color :)
Done | Web update system | Aron |  | c
POUT | Axis number formatting options on graphs (separate for X/Y axes) |  |  | c
Future | Searchable lk function list |  |  | c
Future | Color schemes for graphs - default/dispatch color options |  |  | c
Future | Second Y axis support on graphs |  |  | c
Future | Upgrades to shade BSP algorithm to handle intersecting polygons | Steve |  | c
Future | Implementation of IEC 61853 algorithms in C++ | Aron/Sara | 10 | c
Future | hidden objects should not be included in shade analysis?
Future | remove checkboxes to show/hide objects
Future | zoom to fit, 'F' key
Future | clear properties on de-select object
Future | object list sorted by group
Future | active area polygon rotation
Future | composite objects: regular fixed array
Future | make some macros | Nate
Future | grouping objects, i.e. to create a 'house', can duplicate composite, etc
Future | error message in load calculator when scaling is more than 3x off of raw predicted
Future | DSIRE database linkage | Janine/Aron | 2
Future | Improved native UI behavior on OSX version (i.e. menu bar, etc)
Future | Navigation bar sub texts (array size, location etc)
Future | Internet connection check - display a "not connected message" in welcome box if couldn't connect
Future | Fix output variable group names in SSC so that they show up pretty in outputs browser
Done | Show annual summary statistics (irradiance, wind speed, ambient temp) on the resource page
Future | Average multiple images when importing Solar Pathfinder files | Janine
Future | Report issues: Make report generator available to users, more templates |  |  |  | beta feedback
Future | Curtailment month by hour factors in popup widget thingy | Aron
Future | CSP model bug fixes per AOP | Ty/Mike |  | c
Future | Cavity receiver | Ty/Mike/Steve
Future | Reorganize dispatch widget to UI | Steve
Future | Sample files - esp Novatec - Mike | Mike
Future | Subhourly simulation for physical trough | Aron/Mike
Future | Improve the schedule versus single value button
Future | SNL module page: get rid of temp coeffs and make the a, b, dT more useable
NGTD | .zsam project file importer | Aron/Steve | 10
Post SAM 2014.11.24 Release
Done | Display issues on very high resolution screens (see screenshots from Ted James) | Aron
Done | Change curtailment and availability factors to percentages to be consistent with other losses | Janine
Done | Mystery sam.exe crash on some Windows computers | Aron
Done | Remove lk autosave to avoid junk temporary files | Aron
Done | Add monthly scaling to input hourly load page (monthly scaling available for residential belpe but not commercial) | Janine
Done | Physical trough default T_startup (lowered from 300 to 250 to avoid simulation warnings, but causes 3% annual output reduction) | Steve/Ty
Done | Add LHS and stepwise script functions to LK | Aron
Done | Add parallelized simulation support in script via parsim() and parout() | Aron
Done | Fix alt-by-az shade loss inputs, and test all shade input tables | Janine
Done | Some annual energy values in CSP models use kW units instead of kWh | Paul
Done | Add Royal CSP receivers to physical trough library | Paul
Done | Review CSP time series output variables, e.g., cycle power output appears twice without gross and net designation | Steve/Mike
Done | Make sure all monthly and annual data variables have units | Paul
Done | Fix cash flow spreadsheet so it works with TOD factors, also total installed cost UI labels for all technologies, test for all technologies | Paul
Done | Fix replacement reserve defaults for CSP models: Set to zero | Steve
Done | Fix installer script so that .zsam files open with old SAM and .sam files open with new SAM | Aron
Done | Fix physical trough model to enable subhourly simulations, as in previous versions of SAM | Steve/Ty/Aron | Not for re-release
Done | Remove GCR upper bound of 0.99 to allow values of 1 (and greater than 1) | Janine
Done | Fix single owner IRR convergence and target IRR input of zero issues | Steve/Paul
Not Done | Potential weather file download or unzip issue ("Failed to decompress downloaded weather data" error reported by Chris Richards in support mailbox). Related to internet connectivity issue/proxy settings. | Steve/Aron | Not for re-release
Done | Some combinations of tech/fin displaying incorrect number of columns in cash flow table | Steve
Done | Remove script temporary files ~script (unless SAM crashes or ends abnormally) | Aron
Done | Empirical trough parasitics page user entry bug (values not saved when you leave page) -- also check receivers and other libraries | Paul
Done | Update LK script examples in SDK | Paul/Steve
Done | Solar resource page global horizontal shows 1.#R for international weather files that do not have GHI data | Steve
Done | Test CEC module with user specs (see 2 emails from sam support email) | Paul/Janine
Done | Fix units issue in UI for equipment reserve accounts (dollar amount in UI is off by a factor of 1000) | Paul
Done | Update CSP Generic Thermal storage page to work correctly with TOD factors libarary | Paul/Steve
Done | Fix linear fresnel direct UI bug: Could not evaluate callback function:Linear Fresnel Boiler Geometry->on_load [24]: error in call to 'value()': variable 'csp.lf.sf.azimuth' does not exist in this context[8]: error inside function
Done | Fix dish stirling UI bug: Could not evaluate callback function:Dish Capital Costs->on_load [3]: error in call to 'value()': variable 'case.financing' does not exist in this context
Done | Fix physical trough UI bug: callback function refers to wrong variable name for average focal length | Paul
Done | Fix recapitalization for all technologies and test for geothermal | Steve
Done | Fix swh aux gas macro: convert units from W to kW | Paul
Done | Biopower issues per email from Paul 12/18/14 | Steve
Done | Debt fraction as input to DHF Single Owner and Leveraged Partnership flip | Steve
Not Done | Issue with multiple processor simulations - see scripts from Mark stops around 2700 runs
Done | Financial Model warning and error messages for non-convergence | Steve
Done | Recheck all defaults
Done | Fix WxWidgets date and time bug that causes DView to crash one computers with location set to time zones greater than GMT+7 | Steve
Done | Add gross-to-net conversion factor to CSP models | Ty/Paul
Done | Test mac updater for ssc.dylib and framework | Steve
Done | Fix PV loss autograph on Mac - currently no display | Steve
Done | Recheck all Mac ui forms | Steve
Not Done | Resolve partnership financial model annual cost calculations | Paul/Nate/Steve
Post SAM 2015.1.30 Release |  |  | SVN (SAMnt 1000, ssc 2000) | Move to trunk for update (yes/no)
Done | Fix UI issue with custom HTF min/max temperatures (email with Paul, Ty, and Craig 1/7/2015) | Ty/Paul |  | Yes
Future | Fix stochastic simulations in OS X (lhs.bin fails to load fortran libraries) | Steve/Aron |  | maybe
Done | Improve hourly outputs for utilityrate3 to better show demand charge quantities | Steve/Paul |  | maybe | In progress as of 2/10/2015
Done | Fix OS X save utility rates bug - Save dialog instead of open dialog | Steve |  | (below)
Done | Fix pv report template for cec with user specs, and for weather files with no ghi | Paul |  | (below)
Done | Fix pv report template vmp calculation | Paul |  | (below)
Done | Fix rescom send-to-excel workbook property tax assessed value formula (does not affect cash flow) | Paul |  | (below)
Done | Fix LF tank diameter equation in UI script | Paul |  | Yes
Done | Investigate LF freeze protection potential issue | Ty |  | maybe
Done | Fix bug with custom field and TES HTF | Ty/Paul/Steve |  | Yes
Done | Shift+F5 does not appear to save variable-length arrays to the .lk script | Nick |  | No
Not Done | Add calculated variables to the case compare window | Steve |  | No
Not Done | Belpe documentation | Janine/Sara M |  | No
Done | Fix physical trough collector library so IAM coefficients appear in table (SAMnt) | Paul | 1600 | Yes
Done | Convert physical trough IAM inputs from individual varaibles to array (SAMnt) | Ty | 1596 | No
Done | Fix physical trough receiver library entry for Royal Tech receiver (SAMnt) | Paul | 1595 | Yes
Done | HCPV costs available for parametrics, make HCPV cost group names consistent (SAMnt) | Paul | 1594 | No
Done | Update CSP (physical trough only?) tank volume equation to include dt_hot and dt_cold (SAMnt) | Ty | 1592, | No
Done | Change CSP Storage UI HX derate to HX exergetic efficiency and update equations (SAMnt) | Ty | 1589,1591,1590,1589 | No
Done | #defaults updated for user defined HTFs, storage calculations changes, and array-based IAMs (SAMnt) | Ty | 1597 | No
Done | Excel exchange fixes to work with .xlsm, update SAM inputs with values from Excel (SAMnt) | Steve | 1586 | Yes
Done | added SSC callback function and then on_change() functions that reference the callback in both Solar Field and TES pages to test HTF equivalence. Now setting 'is_hx' in that function, and "hx_derate" is dependent on "is_hx" | Ty | 1585 | No
Done | changed ui names to match ssc and tcs names. documented in SAM TODO | Ty | 1582 | No
Done | #bugfix correct mslf storage tank diameter UI equation | Paul | 1576 | Yes
Done | Fixed typo for Santa Fe NM weather file (was Sata Fe and therefore didn't show up when searching) | Janine | 1575 | Yes
Done | #bugfix rescom send to excel workbook fix error in property tax assessed value equation (forgot to divide percentage by 100). does not affect cash flow results in workbook. | Paul | 1569 | Yes
Done | Added red message warning that inverter had no voltage limits, and hence only one module would be used | Nick | 1567,1614 | No
Done | #bugfix UI changes for custom HTF in physical trough, empirical trough, salt fresnel, and salt tower: Disable edit button for library htf, disable min/max operating temp calculated values for custom htf, update Help topics accordingly. | Paul | 1566 | maybe
Done | #bugfix - project update to fix runtime error on Vista. Tested on Vista and Windows 8. | Steve | 1564 | Done | This may already be in the trunk.
Done | #bugfix shorten registration text so registration information window is less than 600px high -- was preventing people with small screens from registering | Steve/Paul | 1559,1554 | Yes
Done | rename CSP user HTF matrix | Ty | 1557,1556,1555 | No
Done | #bugfix pv report vmp value (change old variable name to new one) | Paul | 1550 | Yes
Done | #new - subarray shading applied based on group number for mxh and diffuse shading. remove beta expiration messages. testing Vista fix for debug processing. | Steve | 1549 | No
Done | Mac build updates | Steve | 1536 | No
Done | Stochastic update to check folder location on Mac | Steve | 1535 | maybe
Done | #ui - update hourly edit dialog to show time step before other buttons for improved work flow as requested by Paul 2/10/15 | Steve | 1529 | No
Done | #bugfix fix issue with pv report template with cec user specified module and for weather files with no ghi data | Paul | 1525 | Yes
Done | #ui update dview labels for load time series variables to be consistent with new ssc output variable labels | Paul | 1524 | maybe
Done | #bugfix generic system cost inputs, fix issues with parametric and group variable properties | Paul | 1518 | Yes
Done | #bugfix - Save rate to file... dialog update per email from Paul and sam support 2/2/15 | Steve | 1517 | Yes
Done | deleted old IAM array TCS_INPUTS and code, updated to accept IAMs reported from UI as a variably-sized matrix instead of fixed, syntax update | Ty | 2595,2594,2593,2592 | No
Done | Custom HTF, HX fixes | Ty | 2567-2588 | maybe
Done | Fixed a bug in Equation 21 from the 2014 wind technical manual. #bugfix | Janine | 2563 | Done
Done | fixed serious bug: sf_type not defined in compute module. this resulted in the solver using the incorrect solution mode and setting the field inlet to the design temperature rather than a recirculated temperature during startup. This resulted in the system "losing" internal energy between timesteps and an artificially low annual energy output. Also, freeze protection energy was not reported in the previous version and is here. | Ty | 2558,2559,2560 | Yes
Done | #bugfix - weather file reader divide by zero if number of records is zero - reported by Paul 2/20/15 | Steve | 2557 | Yes
Done | Update tckernel - add set_unit_value_ssc_... functions to translate from tcs to ssc names per Ty | Steve | 2556 | No
Done | improved error checking on user-defined HTF, corrected to pass UI user defined field fluid property matrix to correct TCS types | Ty | 2543-2553 | No
Done | #new - overloaded set_unit_value_ssc_matrix that take an ssc input matrix of and sets to a tcs matrix with a different name as requested by Ty 2/18/15. Example in cmod_tcsmolten_salt.cpp line 969 | Steve | 2554 | No
Done | deleted old store_fl_props code | Ty | 2555 | No
Done | #ui update load/utility rate output variable names | Paul | 2532 | No
Done | #ui update labels for electric load-related output variables | Paul | 2517 | No
Done | #new - add utility rate output to show peak demand in hour occurs on a TOU period per month basis as requested by Paul 2/6/15 | Steve | 2516 | No
Done | #bugfix - year one sales purchases include TOU demand charges per email from Paul 2/6/15 | Steve | 2515 | Yes
Done | #bugfix - dispatch_calculations class in common_financial.cpp - update to properly handle ppa and degradation inputs and check sizes. Fixes bug reported by Paul 3/12/15 | Steve | 2606 | Yes
Done | change developer.nrel.gov api key to single constant <SAMAPIKEY> in invoke.cpp and update UI and macro scripts that call API. This should solve problems with exceeding api call limits with download electric load macro. | Paul | 1626,1617 | Yes
Done | #bugfix #ui change wind resource file chooser in UI script so it only displays .srw files. Was displaying all weather file extensions even though non-srw files cause wind model simulations to fail. | Paul | 1624 | Yes
Done | #ui Update autographs: PV show monthly energy instead of net dc/ac so graph consistent with annual output and shows effect of loss factors, RESCOM net metering graph move legend to bottom and make bars thicker for better readability. | Paul | 1620 | maybe
Done | #ui fix linear fresnel storage page to disable both min/max operating fluid temp for custom fluid | Paul | 1619 | maybe
Done | #ui add empirical trough custom storage HTF option to make it possible to model direct storage with a custom field HTF | Paul | 1640 | maybe
Done | Fix remaining bug with Wind CSM | Janine |  | Done
Not Done | CEC module library update | Steve |  | Yes
Not Done | Inverter update | Steve |  | Yes
Done | Inverter sizing macro bug fixes | Janine |  | Yes

## Project Ideas
Customizable reports
Trackers for PV should step at discrete angle increments rather than continuously. Not a big issue for 1 hour TS, but at 1 min TS might be a bigger issue
Searchable help system table of contents
Plots for stochastic and p50/p90 simulation outputs
"pinnable" results widgets on summary page - customization of summary page, perhaps with a script widget too
step-by-step interactive debugger for LK language integrated in SAM
import case from another .sam file
Tool to export .sam inputs to SDK
Support for multiple inverter types
Multiple MPPT inputs to an inverter
ITC over multiple years
Simultaneous triple-view in 3D shading tool to help reduce error in scene generation.
3D Shading scene editor: Grouping and duplication of multiple objects simultaneously, with appropriate handling for XYZ coords
Transient thermal models for PV module/array in support of subhourly simulations (realign thermal/mounting structure inputs and standardize across module models)
Direct storage molten salt parabolic trough with freeze-proteciton as thermal energy from TES instead of electrical parasitic (Timo Richert, Flabeg)
HCE loss multiplier for convective and conductive heat losses (Timo Richert, Flabeg)
Excel/VBA interface to SDK (Timo Richert, Flabeg)
Update the location that the proxy.txt file goes and add an indication on the registration page that it found the proxy file | (Registration page indication added in SVN 1324)
Update the model to use MPPT information in the inverter model when using the CEC model
Replace proxy configuration file with a proxy setting with option to enable or disable. See discussion https://sam.nrel.gov/node/69180
Update the LPPA and LCOE metrics to make more sense to end users. Somehow.
Allow ui equations and callbacks to be exported to lk scripts for use with SDK (from Ty).
Make Metrics table more exportable to Excel (commas in numbers convert to column delimiters)
Searchable LK script function list
Customizable metrics table
User Requests (search forum for details)
Cavity receiver for tower models
Make source code available
Display input summary data on navigation menu buttons. Steve's alternative: Display summary from inputs browser in notes window.
Improve weather file checker macro to handle Solar Prospector issues: https://sam.nrel.gov/node/69274#comment-2095
Stochastic simulations for soiling loss: https://sam.nrel.gov/node/69271
Open lk scripts from command line https://sam.nrel.gov/node/69289
Run simulations over periods other than one year (one day, week, etc.) https://sam.nrel.gov/node/69299
LK macros: Scrollbar for long list of UI widgets, UI widget layout and formatting, combined widgets (check box and number) -Nathan Clark, B&V
Gross feed-in tariff (100% system power sold to grid, grid meets 100% of load)
PPA price by year, e.g., 10 PPA agreement at one price, followed by 25 years at another price. Could be implemented as schedule for ppa escalation?

## SAM Variable Changes
Type | Variable Type | Old Name | New Name | Input Page | Default Value (if new) or reason deleted |  | New variable
New variable | array |  | example_new_variable | PV system design | 10 |  | Changed name
Changed name | number | old_variable | changed_variable_example | Degradation |  |  | Deleted variable
Deleted variable | string | bye_bye_variable |  | Wind Costs
New variable | number |  | normalize_to_utility_bill | Electric Load Other | 0 | **** this already existed as a variable on the input page but it wasn't being used- so I don't think it affects the defaults files?
New variable | array |  | utility_bill_data | Electric Load Other | depends on residential vs commercial | ****same as above
Deleted variable |  | p_scale_f |  | Electric Load Other | not used on form
Deleted variable |  | p_offset_value |  | Electric Load Other | not used on form
Changed name | multiple | adjust | adjust | multiple | **CONVENTION CHANGED from derate to loss factor. Values from old files will work, but will be wrong!
New variable | number |  | 6par_aisc_display | CEC Perf model with user entered… | -0.11
New variable | number |  | 6par_bvoc_display | CEC Perf model with user entered… | 0.004
Changed name | matrix | user_defined_htf_array | field_fl_props | Physical Trough Solar Field | Match cmods and tcs names | Ty
Changed name | matrix | csp.dtr.tes.user_htf | store_fl_props | Physical Trough Thermal Storage | Match cmods and tcs names | Ty
Changed name | matrix | user_fluid | store_fl_props | Molten Salt Linear Fresnel Storage | Match cmods and tcs names | Ty
Changed name | number | csp_dtr_sca_iam0_1 | IAMs_1[0] | Physical Trough Collector Type 1 | Allowing table/array of IAM coefficients as inputs | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam1_1 | IAMs_1[1] | Physical Trough Collector Type 1 | Allowing table/array of IAM coefficients as inputs | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam2_1 | IAMs_1[2] | Physical Trough Collector Type 1 | Allowing table/array of IAM coefficients as inputs | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam0_2 | IAMs_2[0] | Physical Trough Collector Type 2 | Allowing table/array of IAM coefficients as inputs | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam1_2 | IAMs_2[1] | Physical Trough Collector Type 2 | Allowing table/array of IAM coefficients as inputs | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam2_2 | IAMs_2[2] | Physical Trough Collector Type 2 | Allowing table/array of IAM coefficients as inputs | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam0_3 | IAMs_3[0] | Physical Trough Collector Type 3 | Allowing table/array of IAM coefficients as inputs | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam1_3 | IAMs_3[1] | Physical Trough Collector Type 3 | Allowing table/array of IAM coefficients as inputs | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam2_3 | IAMs_3[2] | Physical Trough Collector Type 3 | Allowing table/array of IAM coefficients as inputs | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam0_4 | IAMs_4[0] | Physical Trough Collector Type 4 | Allowing table/array of IAM coefficients as inputs | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam1_4 | IAMs_4[1] | Physical Trough Collector Type 4 | Allowing table/array of IAM coefficients as inputs | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam2_4 | IAMs_4[2] | Physical Trough Collector Type 4 | Allowing table/array of IAM coefficients as inputs | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | array | IamF0 | IAM_matrix | Physical Trough Collector Header | combining collector IAM coef. Arrays into 1 output matrix | Ty
Changed name | array | IamF1 | IAM_matrix | Physical Trough Collector Header | combining collector IAM coef. Arrays into 1 output matrix | Ty
Changed name | array | IamF2 | IAM_matrix | Physical Trough Collector Header | combining collector IAM coef. Arrays into 1 output matrix | Ty
Keep track of variable changes in this lovely new table! See examples at the top, contact Janine with questions.

## Unsolved mysteries
Equations/UI mystery bug: total module area calculation doesn't update in the UI in 2014.11.24 release, but works fine in 2015.1.30 release