## Sheet1
Status | What | Who | DAYS | Priority (A/B/C/D) | Additional notes/details
Not done | Case Comparer/Input List/SAM Spreadsheet/Parametrics | Steve/Aron | 3 | a
Done | integration with SAM user registration service | Aron/Rob | 2 | a |  | 39 | A-list
Done | Help system UI and content | Aron/Paul | 8 | a
Done | integration of report generator | Aron/Paul | 3 | a
Done | Scripting (LK) for general replacement of SamUL | Aron/Steve | 4 | a
Done | Solar prospector (download WF) linkage | Janine | 4 | a
Done | Option to not save hourly results | Aron | 0.5 | a
Testing | General usability, including saving views in outputs, graphs | Everyone | 5 | a
Not done | Testing!!! | Everyone | 5 | a
Done | Autographs and metrics tables for each technology | Janine/Steve | 3 | a
Done | Update wxPDFDocument library in WEX to version 0.9.4 | Aron | 0 | a
Done | Expand keyboard shortcuts | Janine | 0.5 | a
Done | Check shading support in pvwatts v5 | Janine | 1 | a
Not done | Update defaults for all cases | ?
Done | Proxy support in SAMnt via proxy.txt | Aron | 0 | a
Not done | Molten salt power tower | Paul | 8 | b |  | 77 | B-list
Not done | Direct steam power tower | Paul | 4 | b
Not done | direct steam linear fresnel | Steve | 4 | b
Not done | molten salt linear fresnel | Steve | 2 | b
Done | csp generic solar | Tom | 2 | b
Not done | SolarPILOT integration | Mike/Aron | 3 | b
Not done | finish up send-to-excel with equations | Steve/? | 2 | b
Done | Excel exchange for base case | Aron | 1.5 | b
Done | update all report templates | Janine/Paul | 5 | b | detailed pv report, basic for all other techs
Not done | OpenEI utility rate database linkage | Aron/Steve | 5 | b
Not done | DSIRE database linkage | Janine/Aron | 2 | b
Not done | Parametrics UI | Aron/Steve | 3 | b
Not done | P50/P90 UI | Aron | 1 | b
Not done | Monte Carlo/LHS (statisical) UI | Aron | 2 | b
Not done | Sensitivity (tornado) UI | Janine | 1 | b
Not done | .zsam project file importer | Aron/Steve | 10 | b
Not done | Integration of 3D shade calculator | Janine/Aron/Steve | 3 | b
Not done | PV self-shading testing | Janine | 1 | b
Not done | Implementation of IEC 61853 algorithms in C++ | Aron/Sara | 10 | b
Not done | building load estimator impl in C++ and integration | Nate/Sara | 5 | b
Not done | Fixes + ui tweaks to tech/market selection dialog | Aron | 0.5 | b
Not done | Change shading factors to shading losses (%) | Janine | ? | b
Not done | Simulation status and warnings dialog box | Aron | 2 | b
Done | HCPV user interface | Tom |  | c
Not done | dish stirling | Tom |  | c
Not done | biomass power |  |  | c
Not done | Wind barriers database linkage |  |  | c
Not done | Parallelized simulation engine |  |  | c
Not done | Upgrades to shade BSP algorithm to handle intersecting polygons |  |  | c
Not done | Access to about dialog/release notes/help - perhaps on welcome/startup page |  |  | c
Not done | Web update system |  |  | c
Not done | Improved native UI behavior on OSX version (i.e. menu bar, etc) |  |  | c
Not done | Second Y axis support on graphs |  |  | c
Not done | Axis number formatting options on graphs (separate for X/Y axes) |  |  | c
Not done | Color schemes for graphs - default/dispatch color options |  |  | c
Not done | Restore "sun-orb" icon? Or keep "flat" metro look & feel |  |  | c
Not done | Navigation bar sub texts (array size, location etc) |  |  | c
Not done | Internet connection check - display a "not connected message" in welcome box if couldn't connect |  |  | c
Not done | Make sure we don't use WX HTTP functions - always use libcurl based wxSimpleCurl class |  |  | c
Not done | CSP model bug fixes per AOP | Ty/Mike |  | c
Not done | Loss diagrams renderer updates and update for tech | Steve |  | c
Not done | Fix zenith angle algorithm not to give junk values at night | Janine |  | c
Not done | Check geothermal financing (lifetime etc)
Not done | Searchable lk function list
Not done | Proxy support fixing