## To Do- FY16 Release
Status | What | Who | Days | Priority (A/B/C/D) | Additional notes/details
Done | Fix todo list formatting issues or fix users. | Janine
Done | Update financial spreadsheets on website for new SAM | Paul
Done | Add back non-net metering, unFIT things | Steve/Paul
Testing | review stack overflow issue when deleting nodes | Aron/Steve/Nick
Testing | Apply various units to utility rates (kWh, horsepower, kcal etc) | Steve
Done | Load and save utility rate data from/to a file | Steve
Done | Add errors for missing irradiance components in weather file if selected on Solar Resource Page | Severin
Done | Add case import feature to bring in cases from other project files | Aron
Done | Fix nighttime hourly AC losses!! Should add to energy draw, not subtract | Janine
Not Done | Follow up on salvage value with Paul S | Janine
Not Done | SDK tool Copy-to-clipboard issues due to changes in wxExtGridCtrl | Aron
Done | Made blade & tower design advanced by default- put something in project file upgrader? | Janine
Done | Other people start adding their to-do items to this list :) | anyone but Janine
Done | Check output timestamp labels for 1-min data | Aron?
Not Done | Send documentation to Paul as needed | All
Done | Show both resource and calculated irradiance outputs | Janine
Not Done | Linear shading option for PV self-shading model (and upgrade project files!) | Janine
Done | Issue with NSRDB downloading files with less than 8760 records | Aron/Anthony
Testing | Hook to the new NSRDB. Fix issue with SAMAPIKEY exceeding rate limit. Put URL in webapi.conf | Aron
Done | remove solar prospector code | aron
In Progress | Hamburger menu! | aron
Testing | Battery automatic dispatch and testing, project file upgrader, etc | Nick
Testing | Finish testing of POA model, project upgrade, documentation | Janine
Done | Updates to utility rate model metering options and input/output structures | Steve/Paul
Done | Proxy autodetection on Windows | Aron
Not Done | Validation and fixes to 3D shading database | Steve/Sara
Not Done | Tweak shading nonlinear loss database UI for public release | Paul
Testing | Remove webkitgtk dependencies on Linux OS, rebuild on CentOS 6.6 as standard | Aron
Done | Wind wizard sensitivity labels are null- fix and also check tornado chart macro | Janine/Aron
Testing | User defined power cycle input option | Ty
Testing | Molten salt power tower model with new controller framework | Ty
Testing | Dispatch optimization for power tower model | Mike
Done | Merge updates from SolarPilot standalone version into SAM, update defaults | Mike
Testing | Check s3d file format reader: does it read old .s3d files OK with group property removed/renamed? Notice in project file upgrader | Steve
Testing | Linux GTK+ version - try bundling built-in theme for standard L&F across platforms | Aron
Done | LK 'global' variable space keyword | Aron
Done | Update LK documentation in line with language changes in VM | Aron
Not Done | JSON read/write functions to write LK objects to disk and retrieve? | Aron
Done | environment scope bug in LK ++/-- operator | Aron
Pre-release | Check all results
Pre-release | Test web update system for all platforms
Pre-release | Check file upgrades from previous versions
Pre-release | Check all default values
Pre-release | Check SDK scripts and samples
Pre-release | OS X form sizing check
Pre-release | Update CEC modules and inverters- check LG module parameters
Pre-release | Release notes
Pre-release | Send Beta to SunEdison, TenK, others?, to make sure it still works for them
Pre-release | Double check UI scaling issues on High DPI screens.
Pre-release | Patch in wxAuiNotebook change: http://trac.wxwidgets.org/ticket/16605#comment:5
Future | Beef up wind model loss outputs, look at TI calculations | Janine
Future | Next release: enable lifetime analysis for no financials (includes moving analysis period into performance models)
Future | Put new NSRDB link at top of Solar Resource page?
Future | Next release: enable seasonally tilted PV systems (macro? Input?)
Future | Evaluate how EES graphs parametric runs | Aron/Steve
Future | Move soiling to shading & snow page and rename "Irradiance Losses", rename loss page "Power Losses" | Paul/Janine
Future | Transformer losses- better representation | Aron
Future | Add simulation warning if negative wind turbine power curve values are input | Janine
Future | BELPE updates | Janine
Future | Reorganize PV outputs (like CSP) | Janine/Paul
Future | p50/p90 better outputs | aron
Future | Year-by-year hourly results from P50/P90 runs | Aron
Future | Checkbox on tower page to update inputs from results based on a script. Add a post-simulation script framework | Aron/Ty
Future | Remove HCPV model and augment simple efficiency model accordingly | Aron
NGTD | Issue with multiple processor simulations - see scripts from Mark stops around 2700 runs | Steve/Aron

## SAM Variable Changes
Type | Variable Type | Old Name | New Name | Input Page | Default Value (if new) or reason deleted | Handled in Version Upgrader? |  | New variable
New variable | array |  | example_new_variable | PV system design | 10 |  |  | Changed name
Changed name | number | old_variable | changed_variable_example | Degradation |  |  |  | Deleted variable
Deleted variable | string | bye_bye_variable |  | Wind Costs
New variable | number |  | normalize_to_utility_bill | Electric Load Other | 0 |  | **** this already existed as a variable on the input page but it wasn't being used- so I don't think it affects the defaults files?
New variable | array |  | utility_bill_data | Electric Load Other | depends on residential vs commercial |  | ****same as above
Deleted variable |  | p_scale_f |  | Electric Load Other | not used on form
Deleted variable |  | p_offset_value |  | Electric Load Other | not used on form
Changed name | multiple | adjust | adjust | multiple | **CONVENTION CHANGED from derate to loss factor. Values from old files will work, but will be wrong!
New variable | number |  | 6par_aisc_display | CEC Perf model with user entered… | -0.11
New variable | number |  | 6par_bvoc_display | CEC Perf model with user entered… | 0.004
Changed name | matrix | user_defined_htf_array | field_fl_props | Physical Trough Solar Field | Match cmods and tcs names | yes | Ty
Changed name | matrix | csp.dtr.tes.user_htf | store_fl_props | Physical Trough Thermal Storage | Match cmods and tcs names | yes | Ty
Changed name | matrix | user_fluid | store_fl_props | Molten Salt Linear Fresnel Storage | Match cmods and tcs names | yes | Ty
Changed name | number | csp_dtr_sca_iam0_1 | IAMs_1[0] | Physical Trough Collector Type 1 | Allowing table/array of IAM coefficients as inputs | yes | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam1_1 | IAMs_1[1] | Physical Trough Collector Type 1 | Allowing table/array of IAM coefficients as inputs | yes | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam2_1 | IAMs_1[2] | Physical Trough Collector Type 1 | Allowing table/array of IAM coefficients as inputs | yes | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam0_2 | IAMs_2[0] | Physical Trough Collector Type 2 | Allowing table/array of IAM coefficients as inputs | yes | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam1_2 | IAMs_2[1] | Physical Trough Collector Type 2 | Allowing table/array of IAM coefficients as inputs | yes | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam2_2 | IAMs_2[2] | Physical Trough Collector Type 2 | Allowing table/array of IAM coefficients as inputs | yes | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam0_3 | IAMs_3[0] | Physical Trough Collector Type 3 | Allowing table/array of IAM coefficients as inputs | yes | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam1_3 | IAMs_3[1] | Physical Trough Collector Type 3 | Allowing table/array of IAM coefficients as inputs | yes | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam2_3 | IAMs_3[2] | Physical Trough Collector Type 3 | Allowing table/array of IAM coefficients as inputs | yes | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam0_4 | IAMs_4[0] | Physical Trough Collector Type 4 | Allowing table/array of IAM coefficients as inputs | yes | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam1_4 | IAMs_4[1] | Physical Trough Collector Type 4 | Allowing table/array of IAM coefficients as inputs | yes | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | number | csp_dtr_sca_iam2_4 | IAMs_4[2] | Physical Trough Collector Type 4 | Allowing table/array of IAM coefficients as inputs | yes | Ty If IAM beceoms available in User Library, may want to make values array instead of set at 3 variables
Changed name | array | IamF0 | IAM_matrix | Physical Trough Collector Header | combining collector IAM coef. Arrays into 1 output matrix | N/A | Ty
Changed name | array | IamF1 | IAM_matrix | Physical Trough Collector Header | combining collector IAM coef. Arrays into 1 output matrix | N/A | Ty
Changed name | array | IamF2 | IAM_matrix | Physical Trough Collector Header | combining collector IAM coef. Arrays into 1 output matrix | N/A | Ty
New variable | number |  | activate_snow_model | PV Shading | 0 |  | Severin
Deleted variable | number | csp.pt.tes.dry_loss_coeff |  | Molten Salt Tower Storage | Not used in performance code or ui calcs | N/A | Ty
Changed name | number | tank_max_heat | hot_tank_max_heat | Molten Salt Tower Storage | need to differentiate between hot and cold tank names | yes | Ty
Changed name | number | csp.pt.tes.cold_heater_max_load | cold_tank_max_heat | Molten Salt Tower Storage | Match cmods and tcs names | yes | Ty
Deleted variable | number | csp.pt.tes.storage_bypass |  | Molten Salt Tower Storage | Bypass N/A for tower because storage HTF = rec/pc HTF (no storage HX) | N/A | Ty
Deleted variable | number | tes_pump_coef |  | Molten Salt Tower Parasitics | storage HTF = rec/pc HTF (no storage HX), so no pumping losses | N/A | Ty
Deleted variable | number | P_storage_pump |  | Molten Salt Tower Parasitics | storage HTF = rec/pc HTF (no storage HX), so no pumping losses | N/A | Ty
Deleted variable | number | storage_bypass |  | Molten Salt Tower Parasitics | storage HTF = rec/pc HTF (no storage HX), so no pumping losses | N/A | Ty
Deleted variable | number | recirc_source |  | Molten Salt Tower Parasitics | not used | N/A | Ty
Deleted variable | number | recirc_htf_eff |  | Molten Salt Tower Parasitics | not used | N/A | Ty
Deleted variable | number | flow_from_storage |  | Molten Salt Tower Parasitics | not used | N/A | Ty
Deleted variable | number | P_hot_tank |  | Molten Salt Tower Parasitics | not used | N/A | Ty
Deleted variable | number | csp.pt.par.bop_c1 |  | Molten Salt Tower Parasitics | not used | N/A | Ty
Deleted variable | number | P_storage_pump |  | Direct Steam Tower Parasitics | not used | N/A | Ty
Deleted variable | number | P_hot_tank |  | Direct Steam Tower Parasitics | not used | N/A | Ty
Deleted variable | number | recirc_source |  | Direct Steam Tower Parasitics | not used | N/A | Ty
Deleted variable | number | storage_bypass |  | Direct Steam Tower Parasitics | not used | N/A | Ty
Deleted variable | number | recirc_htf_eff |  | Direct Steam Tower Parasitics | not used | N/A | Ty
Deleted variable | number | flow_from_storage |  | Direct Steam Tower Parasitics | not used | N/A | Ty
Deleted variable | number | rec_htf_flow |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | ref_htf_flow |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | P_cold_tank |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | P_tower_conv |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | P_tower_rad |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | P_htf_pump |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | night_recirc |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | mode |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | th_fin |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | l_fin |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | emis_fin |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | abs_fin |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | mat_fin |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | abs_boiler |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | emis_sh |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | abs_sh |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | emis_rh |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | number | abs_rh |  | Direct Steam Tower Receiver | not used | N/A | Ty
Deleted variable | array | aux_array |  | Molten Salt Tower Parasitics | not used | N/A | Ty
Deleted variable | array | bop_array |  | Molten Salt Tower Parasitics | not used | N/A | Ty
Deleted variable | number | m_dot_htf_ref |  | Molten Salt Tower Power Block | not used | N/A | Ty
Deleted variable | number | T_pb_out |  | Molten Salt Tower Power Block | not used | N/A | Ty
Deleted variable | number | mode |  | Molten Salt Tower Power Block | not used | N/A | Ty
Deleted variable | number | fthr_ok |  | Molten Salt Tower Power Block | not used | N/A | Ty
Deleted variable | number | pb_fixed_par_cntl |  | Molten Salt Tower Power Block | not used | N/A | Ty
Deleted variable | number | dt_cold |  | Molten Salt Tower Power Block | not used | N/A | Ty
Deleted variable | number | dt_hot |  | Molten Salt Tower Power Block | not used | N/A | Ty
Deleted variable | number | hx_config |  | Molten Salt Tower Power Block | not used | N/A | Ty
Deleted variable | number | is_hx |  | Molten Salt Tower Power Block | not used | N/A | Ty
Deleted variable | number | tech_type |  | Molten Salt Tower Power Block | not used | N/A | Ty
Deleted variable | number | deg_wind |  | Molten Salt Tower Receiver | not used | N/A | Ty
Deleted variable | number | P_htf |  | Molten Salt Tower Receiver | not used | N/A | Ty
Deleted variable | number | T_salt_cold |  | Molten Salt Power Block | not used | N/A | Ty
Deleted variable | number | HTF |  | Molten Salt Power Block | not used | N/A | Ty
Deleted variable | number | Design_power |  | Molten Salt Power Block | not used | N/A | Ty
Deleted variable | number | csp.pt.pwrb.min_restart_time |  | Molten Salt Power Block | not used | N/A | Ty
Deleted variable | number | csp.pt.rec.max_rec_flux |  | Molten Salt Power Block | not used | N/A | Ty
Deleted variable | number | store_fluid |  | Molten Salt Tower Storage | not used | N/A | Ty
Deleted variable | number | csp.dst.pipe_c0 |  | Direct Steam Tower Parasitics | redundant - different variable used in compute module | N/A | Ty
Deleted variable | number | csp.dst.pipe_c1 |  | Direct Steam Tower Parasitics | redundant - different variable used in compute module | N/A | Ty
Changed name | number | csp.pt.par.piping_length_const | piping_length_mult | Direct Steam Tower Parasitics | variables were incorrectly switched in old version - would only impact simulations that performed real-time tower height optimization | Yes | Ty
Changed name | number | csp.pt.par.piping_length_mult | piping_length_add | Direct Steam Tower Parasitics | variables were incorrectly switched in old version - would only impact simulations that performed real-time tower height optimization | Yes | Ty
Changed name | number | emis_boiler | rec_emis | Direct Steam Tower Receiver | User-input emissivity used for boiler/sh/rh | Yes | Ty

## Future Ideas
Status | What | Who | DAYS | Priority (A/B/C/D) | Additional notes/details
POUT | Better weather file reader error reporting for EPW files from IWEC that have zeros for dew-point temperatures | Aron |  |  | beta feedback
POUT | Text bigger than buttons when Windows display settings to more than 100% |  |  |  | beta feedback
Future | Move all CSP constants from ui to respective compute modules | Steve
POUT | Axis number formatting options on graphs (separate for X/Y axes) |  |  | c
Future | Searchable lk function list |  |  | c
Future | Color schemes for graphs - default/dispatch color options |  |  | c
Future | Second Y axis support on graphs |  |  | c
Future | Upgrades to shade BSP algorithm to handle intersecting polygons | Steve |  | c
Future | hidden objects should not be included in shade analysis?
Future | remove checkboxes to show/hide objects
Future | zoom to fit, 'F' key
Future | clear properties on de-select object
Future | object list sorted by group
Future | active area polygon rotation
Future | composite objects: regular fixed array
Future | grouping objects, i.e. to create a 'house', can duplicate composite, etc
Future | error message in load calculator when scaling is more than 3x off of raw predicted
Future | DSIRE database linkage | Janine/Aron | 2
Future | Improved native UI behavior on OSX version (i.e. menu bar, etc)
Future | Navigation bar sub texts (array size, location etc)
Future | Internet connection check - display a "not connected message" in welcome box if couldn't connect
Future | Fix output variable group names in SSC so that they show up pretty in outputs browser
Future | Report issues: Make report generator available to users, more templates |  |  |  | beta feedback
Future | Curtailment month by hour factors in popup widget thingy | Aron
Future | CSP model bug fixes per AOP | Ty/Mike |  | c
Future | Cavity receiver | Ty/Mike/Steve
Future | Reorganize dispatch widget to UI | Steve
Future | Sample files - esp Novatec - Mike | Mike
Future | Subhourly simulation for physical trough | Aron/Mike
Future | Improve the schedule versus single value button
Future | SNL module page: get rid of temp coeffs and make the a, b, dT more useable
NGTD | .zsam project file importer | Aron/Steve | 10
Future | stacked LCOE macro
Future | monthly fixed tilt
Future | Third party ownership: add partial prepaid and prepaid leases
Future | Third party ownership: change "after-tax annual costs" to "annual cost" and remove "agreement cost", show costs as negative | Steve/Janine
Future | Evaluate how EES graphs parametrics- can we do the same?

## Project Ideas
Customizable reports
Trackers for PV should step at discrete angle increments rather than continuously. Not a big issue for 1 hour TS, but at 1 min TS might be a bigger issue
Searchable help system table of contents
Plots for stochastic and p50/p90 simulation outputs
"pinnable" results widgets on summary page - customization of summary page, perhaps with a script widget too
step-by-step interactive debugger for LK language integrated in SAM
import case from another .sam file
Tool to export .sam inputs to SDK
Support for multiple inverter types
Multiple MPPT inputs to an inverter
ITC over multiple years
Simultaneous triple-view in 3D shading tool to help reduce error in scene generation.
3D Shading scene editor: Grouping and duplication of multiple objects simultaneously, with appropriate handling for XYZ coords
Transient thermal models for PV module/array in support of subhourly simulations (realign thermal/mounting structure inputs and standardize across module models)
Direct storage molten salt parabolic trough with freeze-proteciton as thermal energy from TES instead of electrical parasitic (Timo Richert, Flabeg)
HCE loss multiplier for convective and conductive heat losses (Timo Richert, Flabeg)
Excel/VBA interface to SDK (Timo Richert, Flabeg)
Update the location that the proxy.txt file goes and add an indication on the registration page that it found the proxy file | (Registration page indication added in SVN 1324)
Update the model to use MPPT information in the inverter model when using the CEC model
Replace proxy configuration file with a proxy setting with option to enable or disable. See discussion https://sam.nrel.gov/node/69180
Update the LPPA and LCOE metrics to make more sense to end users. Somehow.
Allow ui equations and callbacks to be exported to lk scripts for use with SDK (from Ty).
Make Metrics table more exportable to Excel (commas in numbers convert to column delimiters)
Searchable LK script function list
Customizable metrics table
User Requests (search forum for details)
Cavity receiver for tower models
Make source code available
Display input summary data on navigation menu buttons. Steve's alternative: Display summary from inputs browser in notes window.
Improve weather file checker macro to handle Solar Prospector issues: https://sam.nrel.gov/node/69274#comment-2095
Stochastic simulations for soiling loss: https://sam.nrel.gov/node/69271
Open lk scripts from command line https://sam.nrel.gov/node/69289
Run simulations over periods other than one year (one day, week, etc.) https://sam.nrel.gov/node/69299
LK macros: Scrollbar for long list of UI widgets, UI widget layout and formatting, combined widgets (check box and number) -Nathan Clark, B&V
Gross feed-in tariff (100% system power sold to grid, grid meets 100% of load)
PPA price by year, e.g., 10 PPA agreement at one price, followed by 25 years at another price. Could be implemented as schedule for ppa escalation?
SolarPilot add maximum tower height to restrict optimization https://sam.nrel.gov/node/69394, Mike Wagner email 4/27/2015
Report tower flux map as output https://sam.nrel.gov/node/69393, Mike Wagner email 4/27/2015
Full simulation for each year to model module degradation and clipping inverters (https://sam.nrel.gov/node/69400)

## Unsolved mysteries
Equations/UI mystery bug: total module area calculation doesn't update in the UI in 2014.11.24 release, but works fine in 2015.1.30 release

## To Do- FY15 Release (old)
Status | What | Who | Days | Priority (A/B/C/D) | Additional notes/details
Not Done | Issue with multiple processor simulations - see scripts from Mark stops around 2700 runs | Steve/Aron |  | A
Done | Resolve partnership financial model annual cost calculations | Paul |  | A
Done | Diffuse view factor from shade tool instead of irradiation processor | Steve |  | A
Done | Update SAM upgrade script for PV variable changes | Janine |  | A
Done | Update SAM upgrade script for CSP variable changes | Ty |  | A
Done | Update SAM upgrade script for all battery/lifetime variables | Nick |  | A
Done | Nate's parametric bug | Steve |  | A
Done | TYA files in SAM | Severin |  | A
Done | utility rate: monthly vs hourly reconciliation | Steve/Paul |  | A
Done | LCOE calculator | Paul |  | A
Done | Battery model | Nick |  | A
Done | Power electronics buttons | Janine |  | A
Done | Snow model finalization | Severin/Janine |  | A
Done | Third Party Ownership | Janine/Nate |  | A
Done | Fix bug in performance ratio | Janine |  | A
Done | Fix single owner end-to-excel to work with fixed debt fraction option | Paul
Done | Make an awesome to-do list for our June release | Janine |  | A
NGTD | Potential weather file download or unzip issue ("Failed to decompress downloaded weather data" error reported by Chris Richards in support mailbox). Related to internet connectivity issue/proxy settings. | Steve/Aron |  | B
NGTD | Rate/load misalignment resolution | Nate/Janine |  | B | issue per Nate Clark email
Done | IEC 61853 model | Aron |  | B
Done | Snow model conversion macro | Severin |  | B
Done | Dealing with leap days | Severin/Janine |  | B
Done | Inverter warning message bug | Nick |  | B
Done | Siting considerations macro bug | Janine |  | B
Done | Bug in wind layout import | Janine |  | B
Future | Belpe documentation | Sara/Janine |  | C
Done | Remove solar pathfinder second button | Severin |  | C | Request per Oliver Hellwig
Done | negative salvage values | Severin |  | C
Done | Import multiple images from Solar Pathfinder | Severin |  | C
Done | Add SolarAnywhere to weather file converter macro | Paul |  | C
Done | Check the reports | Janine
Done | Check the macros | Janine
Pre-release | Check all results
Pre-release | Test web update system for all platforms | Aron
Pre-release | Check all default values | Aron
Pre-release | Check SDK scripts and samples
Pre-release | OS X form sizing check | Aron
Pre-release | Update CEC modules and inverters | Steve
Pre-release | Release notes | Aron
Done | Fix tech/market window help | Paul
Done | New battery storage help topics | Paul/Nick
Done | New third party financing help | Paul/Steve
Done | New LCOE calculator help | Paul
Future | Update financial spreadsheets on website for new SAM | Paul
Done | Update registration proxy instructions in help | Paul
Done | Revise weather file format topic to only describe SAM CSV and SRW | Paul
Done | Power tower help review and revision | Paul
Done | Physical trough help review and revision | Paul
Done | LCOE and financial metrics review and revision | Paul
Done | Update electricity rates help for monthly/hourly reconciliation | Paul
done | Loss diagram fixes | Steve
done | Utility rate updates/battery tests | Steve
Done | battery macro tests and dc connected battery loss diagram for inverter efficiency | Nick/Steve
Done | Check updater | Ty/Aron
Done | Decouple the transposition model from the 3D shading model for diffuse | Aron
Not Done | Add back non-net metering, unFIT things | Steve/Paul
Done | High DPI screens | Aron

## To Do- FY14 Release (old)
Status | What | Who | DAYS | Priority (A/B/C/D) | Additional notes/details
Done | Case Comparer/Input List/SAM Spreadsheet/Parametrics | Steve/Aron | 3 | a
Done | integration with SAM user registration service | Aron/Rob | 2 | a |  | 39 | A-list
Done | Help system UI and content | Aron/Paul | 8 | a
Done | integration of report generator | Aron/Paul | 3 | a
Done | Scripting (LK) for general replacement of SamUL | Aron/Steve | 4 | a
Done | Solar prospector (download WF) linkage | Janine | 4 | a
Done | Option to not save hourly results | Aron | 0.5 | a
Done | General usability, including saving views in outputs, graphs | Everyone | 5 | a
Done | Testing!!! | Everyone | 5 | a
Done | Autographs and metrics tables for each technology | Janine/Steve | 3 | a
Done | Update wxPDFDocument library in WEX to version 0.9.4 | Aron | 0 | a
Done | Expand keyboard shortcuts | Janine | 0.5 | a
Done | Check shading support in pvwatts v5 | Janine | 1 | a
Done | Update defaults for all cases | ? |  | a
Done | Proxy support in SAMnt via proxy.txt | Aron | 0 | a
Done | csp generic solar | Tom | 2 | b
Done | Excel exchange for base case | Aron | 1.5 | b
Done | update all report templates | Paul | 5 | b | detailed pv report, basic for all other techs
Done | OpenEI utility rate database linkage | Aron/Steve | 5 | b
Done | Parametrics UI | Aron/Steve | 3 | b
Done | P50/P90 UI | Aron | 1 | b
Done | Monte Carlo/LHS (statisical) UI | Aron | 2 | b
Done | Macro system UI | Janine | 1 | b
Done | Integration of 3D shade calculator | Janine/Aron/Steve | 3 | b
Done | PV self-shading testing | Janine | 1 | b
Done | Re-arrange self-shading inputs in UI with system design? Sizing check? Check inputs for usability in SDK | Janine |  | b
Done | building load estimator impl in C++ and integration | Nate/Sara | 5 | b
Done | Fixes + ui tweaks to tech/market selection dialog | Aron | 0.5 | b
Done | Change shading factors to shading losses (%) | Janine |  | b
Done | Save DView timeseries state between simulations - i.e. restore checked values and graph axes | Aron |  | b
Done | Check SunEye Obstructions and both Solar Pathfinder file imports | Janine |  | b
Done | Simulation status and warnings dialog box | Aron | 2 | b
Done | Weather file settings dialog to set search path and download folder, rescan library, updates to UI | Aron |  | b
Done | HCPV user interface | Tom |  | c
Done | Molten salt power tower | Steve | 8 | b |  | 32 | B-list
Done | dish stirling | Tom |  | c
Done | SolarPILOT integration | Mike/Aron | 3 | b
Done | finish up send-to-excel with equations | Paul | 2 | b
Done | List of alpha feedback from Nate |  |  | b
Done | biomass power | Tom |  | c
Done | Wind barriers database linkage | Janine |  | c
Done | Parallelized simulation engine | Aron |  | c
Done | Access to about dialog/release notes/help - perhaps on welcome/startup page | Aron |  | c
Done | Restore "sun-orb" icon? Or keep "flat" metro look & feel | Aron |  | c
Done | Make sure we don't use WX HTTP functions - always use libcurl based wxSimpleCurl class |  |  | c
Done | Loss diagrams renderer updates and update for tech | Steve |  | c
Done | Fix zenith angle algorithm not to give junk values at night | Janine |  | c
Done | Check geothermal financing (lifetime etc) | Steve |  | c
Done | Proxy support fixing, potentially autodetection on Windows? |  |  | c
Done | Mac forms |  |  | c
Done | Defaults manager for updating default values in various configurations | Aron |  | c
Done | Direct steam power tower | Steve | 4 | c
Done | direct steam linear fresnel | Tom | 4 | c
Done | molten salt linear fresnel | Tom | 2 | c
Done | Re-export libraries from old SAM | Janine |  | c
Done | Fix output variable group names in SSC: Flat Plate, PVWatts, Wind, CSP Trough & Towers, Res, Comm | Janine
Done | Janine has to fix what Aron broke in the Macros | Janine
Done | Janine can sort TODO list | Janine
Done | Tower fixes - Steve & Mike | Steve/Mike
Done | Steam tower | Ty/Steve
Done | Molten salt linear fresnel - match with script from Ty | Steve
Done | Clean up the multiple load metrics reported to UI |  |  | c
Done | Wind - cost and scaling model | Tom
Done | Review default values, financial, cost #s for PV res/com/util | Everyone
Done | Documentation updates from Paul | Paul
Done | Progress updates for solarpilot - Aron | Aron
Done | Add performance adjustment factors to wind model | Janine/Aron
Done | Possible registration issues
Done | Fix issue with InnoSetup uninstall win32 and x64 - windows 7 and window 8 | Steve |  |  | beta feedback
Done | UI text to explain URDB utility name aliasing issue (e.g., PG&E appears in list but without rates) | Paul |  |  | beta feedback
Done | Add time stamp column to time series data exported from data tables to Excel/CSV, also from time series data viewer if possible | Aron |  |  | beta feedback
Done | Weather file summary statistics on climate pages (total DNI, GHI, DHI in kWh/m2 and/or kWh/m2/day, average dry-bulb temperature, average wind speed) | Aron calculations, Paul UI |  |  | beta feedback
Done | Tool for populating ranges of parametric input variable values | Aron/Steve |  |  | beta feedback
Done | Investigate SWH model without electric load pages | Aron
Done | HCPV model: add option for irradiance table to be DNI based rather than cell POA based | Aron
Done | Registration pop-up window to explain what data NREL is collecting and why, with option to exit without registering | Aron |  |  | beta feedback
Done | Continue debugging time series data viewer |  |  |  | beta feedback
Done | Single owner send to excel dscr=0 divide by zero issue | Paul |  |  | beta feedback
Done | Issue entering values on computers with language setting other than U.S. English | Aron |  |  | beta feedback
Done | SHIFT issue with TMY2 weather files causes CSP models to crash | Aron |  |  | beta feedback
Done | Startup issues for computers with right-to-left reading order | Aron |  |  | beta feedback, possible fix with WxWidgets update
Done | direct steam tower: receiver height calculated value is zero |  |  |  | H_rec and rec_height variables in UI, H_rec in ssc
Done | biopower: feedstock download buttons do not work | Aron
Done | geothermal: Lookup temp and depth button does not work | Aron
Done | SDK build | Steve
Done | CEC Inverter updates | Steve
Done | PBNS update for dispatch factors | Steve
Done | Fix issue with parametric grid editor read only display of monthly and hourly outputs.
Pre-release | Check the reports | Everyone
Pre-release | Check the macros | Everyone
Pre-release | Check all results, and summarize for release notes | Everyone
Pre-release | Check all default values | Everyone
Done | Vote against that horrible marigold color :)
Done | Web update system | Aron |  | c
Done | Show annual summary statistics (irradiance, wind speed, ambient temp) on the resource page
Post SAM 2014.11.24 Release
Done | Display issues on very high resolution screens (see screenshots from Ted James) | Aron
Done | Change curtailment and availability factors to percentages to be consistent with other losses | Janine
Done | Mystery sam.exe crash on some Windows computers | Aron
Done | Remove lk autosave to avoid junk temporary files | Aron
Done | Add monthly scaling to input hourly load page (monthly scaling available for residential belpe but not commercial) | Janine
Done | Physical trough default T_startup (lowered from 300 to 250 to avoid simulation warnings, but causes 3% annual output reduction) | Steve/Ty
Done | Add LHS and stepwise script functions to LK | Aron
Done | Add parallelized simulation support in script via parsim() and parout() | Aron
Done | Fix alt-by-az shade loss inputs, and test all shade input tables | Janine
Done | Some annual energy values in CSP models use kW units instead of kWh | Paul
Done | Add Royal CSP receivers to physical trough library | Paul
Done | Review CSP time series output variables, e.g., cycle power output appears twice without gross and net designation | Steve/Mike
Done | Make sure all monthly and annual data variables have units | Paul
Done | Fix cash flow spreadsheet so it works with TOD factors, also total installed cost UI labels for all technologies, test for all technologies | Paul
Done | Fix replacement reserve defaults for CSP models: Set to zero | Steve
Done | Fix installer script so that .zsam files open with old SAM and .sam files open with new SAM | Aron
Done | Fix physical trough model to enable subhourly simulations, as in previous versions of SAM | Steve/Ty/Aron | Not for re-release
Done | Remove GCR upper bound of 0.99 to allow values of 1 (and greater than 1) | Janine
Done | Fix single owner IRR convergence and target IRR input of zero issues | Steve/Paul
Done | Some combinations of tech/fin displaying incorrect number of columns in cash flow table | Steve
Done | Remove script temporary files ~script (unless SAM crashes or ends abnormally) | Aron
Done | Empirical trough parasitics page user entry bug (values not saved when you leave page) -- also check receivers and other libraries | Paul
Done | Update LK script examples in SDK | Paul/Steve
Done | Solar resource page global horizontal shows 1.#R for international weather files that do not have GHI data | Steve
Done | Test CEC module with user specs (see 2 emails from sam support email) | Paul/Janine
Done | Fix units issue in UI for equipment reserve accounts (dollar amount in UI is off by a factor of 1000) | Paul
Done | Update CSP Generic Thermal storage page to work correctly with TOD factors libarary | Paul/Steve
Done | Fix linear fresnel direct UI bug: Could not evaluate callback function:Linear Fresnel Boiler Geometry->on_load [24]: error in call to 'value()': variable 'csp.lf.sf.azimuth' does not exist in this context[8]: error inside function
Done | Fix dish stirling UI bug: Could not evaluate callback function:Dish Capital Costs->on_load [3]: error in call to 'value()': variable 'case.financing' does not exist in this context
Done | Fix physical trough UI bug: callback function refers to wrong variable name for average focal length | Paul
Done | Fix recapitalization for all technologies and test for geothermal | Steve
Done | Fix swh aux gas macro: convert units from W to kW | Paul
Done | Biopower issues per email from Paul 12/18/14 | Steve
Done | Debt fraction as input to DHF Single Owner and Leveraged Partnership flip | Steve
Done | Financial Model warning and error messages for non-convergence | Steve
Done | Recheck all defaults
Done | Fix WxWidgets date and time bug that causes DView to crash one computers with location set to time zones greater than GMT+7 | Steve
Done | Add gross-to-net conversion factor to CSP models | Ty/Paul
Done | Test mac updater for ssc.dylib and framework | Steve
Done | Fix PV loss autograph on Mac - currently no display | Steve
Done | Recheck all Mac ui forms | Steve
Post SAM 2015.1.30 Release |  |  | SVN (SAMnt 1000, ssc 2000) | Move to trunk for update (yes/no)
Done | CSP with custom HTF: disable min/max operating temperatures to minimize user confusion. For library HTFs, these are hard-coded in the UI so they are not available for custom HTFs. (email with Paul, Ty, and Craig 1/7/2015) | Ty/Paul |  | No
Done | Fix stochastic simulations in OS X (lhs.bin fails to load fortran libraries) | Steve/Aron |  | Done | Binary builds for mac only - checked in 2015.1.30 branch SAMnt rev 1656
Done | Improve hourly outputs for utilityrate3 to better show demand charge quantities | Steve/Paul |  | maybe | In progress as of 2/10/2015
Done | Fix OS X save utility rates bug - Save dialog instead of open dialog | Steve |  | Done | Checked in trunk and 2015.1.30 branch SAMnt rev 1665
Done | Fix pv report template for cec with user specs, and for weather files with no ghi | Paul |  | (below)
Done | Fix pv report template vmp calculation | Paul |  | (below)
Done | Fix rescom send-to-excel workbook property tax assessed value formula (does not affect cash flow) | Paul |  | (below)
Done | Fix bug with custom field and TES HTF | Ty/Paul/Steve |  | Done | In 2015.1.30 branch, Subject to review by Paul, see email from Steve 3/21/15
Done | Shift+F5 does not appear to save variable-length arrays to the .lk script | Nick |  | No
Done | Add calculated variables to the case compare window | Steve |  | No | Checked in SAMnt rev 1722
Done | Fix physical trough collector library so IAM coefficients appear in table (SAMnt) | Paul | 1600 | No | This should be changed with the revision in SVN 1596
Done | Convert physical trough IAM inputs from individual varaibles to array (SAMnt) | Ty | 1596 | No
Done | Fix physical trough receiver library entry for Royal Tech receiver (SAMnt) | Paul | 1595 | Done
Done | HCPV costs available for parametrics, make HCPV cost group names consistent (SAMnt) | Paul | 1594 | No
Done | Update CSP (physical trough only?) tank volume equation to include dt_hot and dt_cold (SAMnt) | Ty | 1592, | No
Done | Change CSP Storage UI HX derate to HX exergetic efficiency and update equations (SAMnt) | Ty | 1589,1591,1590,1589 | No
Done | #defaults updated for user defined HTFs, storage calculations changes, and array-based IAMs (SAMnt) | Ty | 1597 | No
Done | Excel exchange fixes to work with .xlsm, update SAM inputs with values from Excel (SAMnt) | Steve | 1586 | Done | Checked in 2015.1.30 branch SAMnt svn rev 1656
Done | added SSC callback function and then on_change() functions that reference the callback in both Solar Field and TES pages to test HTF equivalence. Now setting 'is_hx' in that function, and "hx_derate" is dependent on "is_hx" | Ty | 1585 | No
Done | changed ui names to match ssc and tcs names. documented in SAM TODO | Ty | 1582 | No
Done | #bugfix correct mslf storage tank diameter UI equation | Paul | 1576 | Done | In 2015.1.30 branch, Subject to review by Paul, see email from Steve 3/21/15
Done | Fixed typo for Santa Fe NM weather file (was Sata Fe and therefore didn't show up when searching) | Janine | 1575 | Done
Done | #bugfix rescom send to excel workbook fix error in property tax assessed value equation (forgot to divide percentage by 100). does not affect cash flow results in workbook. | Paul | 1569 | Done
Done | Added red message warning that inverter had no voltage limits, and hence only one module would be used | Nick | 1567,1614 | Done | In 2015.1.30 branch, verified works
Done | #bugfix UI changes for custom HTF in physical trough, empirical trough, salt fresnel, and salt tower: Disable edit button for library htf, disable min/max operating temp calculated values for custom htf, update Help topics accordingly. | Paul | 1566 | maybe | Done except for disabling min/max operating temps when they are set to zero.
Done | #bugfix - project update to fix runtime error on Vista. Tested on Vista and Windows 8. | Steve | 1564 | Done | Already in 2015.1.30 branch and in trunk
Done | #bugfix shorten registration text so registration information window is less than 600px high -- was preventing people with small screens from registering | Steve/Paul | 1559,1554 | Done | Checked in 2015.1.30 branch SAMnt svn rev 1657
Done | rename CSP user HTF matrix | Ty | 1557,1556,1555 | No
Done | #bugfix pv report vmp value (change old variable name to new one) | Paul | 1550 | Done
Done | #new - subarray shading applied based on group number for mxh and diffuse shading. | Steve | 1549 | No
Done | testing Vista fix for debug processing. | Steve | 1549 | Done
Done | remove beta expiration messages. | Steve | 1549 | Done
Done | Mac build updates | Steve | 1536 | Done
Done | Stochastic update to check folder location on Mac | Steve | 1535 | Done | Checked in trunk and 2015.1.30 branch SAMnt rev 1665
Done | #ui - update hourly edit dialog to show time step before other buttons for improved work flow as requested by Paul 2/10/15 | Steve | 1529 | Done | Checked in 2015.1.30 branch SAMnt svn rev 1659
Done | #bugfix fix issue with pv report template with cec user specified module and for weather files with no ghi data | Paul | 1525 | Done
Done | #ui update dview labels for load time series variables to be consistent with new ssc output variable labels | Paul | 1524 | maybe
Done | #bugfix generic system cost inputs, fix issues with parametric and group variable properties | Paul | 1518 | Done
Done | #bugfix - Save rate to file... dialog update per email from Paul and sam support 2/2/15 | Steve | 1517 | Done | Checked in trunk and 2015.1.30 branch SAMnt rev 1665
Done | deleted old IAM array TCS_INPUTS and code, updated to accept IAMs reported from UI as a variably-sized matrix instead of fixed, syntax update | Ty | 2595,2594,2593,2592 | No
Done | Custom HTF, HX fixes | Ty | 2567-2588 | maybe
Done | Fixed a bug in Equation 21 from the 2014 wind technical manual. #bugfix | Janine | 2563 | Done
Done | MSLF: fixed serious bug: sf_type not defined in compute module. this resulted in the solver using the incorrect solution mode and setting the field inlet to the design temperature rather than a recirculated temperature during startup. This resulted in the system "losing" internal energy between timesteps and an artificially low annual energy output. Also, freeze protection energy was not reported in the previous version and is here. | Ty | 2558,2559,2560 | Done | In 2015.1.30 branch, Subject to review by Paul, see email from Steve 3/21/15
Done | #bugfix - weather file reader divide by zero if number of records is zero - reported by Paul 2/20/15 | Steve | 2557 | Done | Checked in 2015.1.30 branch ssc svn rev 2620
Done | Update tckernel - add set_unit_value_ssc_... functions to translate from tcs to ssc names per Ty | Steve | 2556 | No
Done | improved error checking on user-defined HTF, corrected to pass UI user defined field fluid property matrix to correct TCS types | Ty | 2543-2553 | No
Done | #new - overloaded set_unit_value_ssc_matrix that take an ssc input matrix of and sets to a tcs matrix with a different name as requested by Ty 2/18/15. Example in cmod_tcsmolten_salt.cpp line 969 | Steve | 2554 | No
Done | deleted old store_fl_props code | Ty | 2555 | No
Done | #ui update load/utility rate output variable names | Paul | 2532 | maybe
Done | #ui update labels for electric load-related output variables | Paul | 2517 | maybe
Done | #new - add utility rate output to show peak demand in hour occurs on a TOU period per month basis as requested by Paul 2/6/15 | Steve | 2516 | No
Done | #bugfix - year one sales purchases include TOU demand charges per email from Paul 2/6/15 | Steve | 2515 | done | Checked in 2015.1.30 branch ssc svn rev 2621
Done | #bugfix - dispatch_calculations class in common_financial.cpp - update to properly handle ppa and degradation inputs and check sizes. Fixes bug reported by Paul 3/12/15 | Steve | 2606 | Done | Checked in 2015.1.30 branch ssc svn rev 2627
Done | change developer.nrel.gov api key to single constant <SAMAPIKEY> in invoke.cpp and update UI and macro scripts that call API. This should solve problems with exceeding api call limits with download electric load macro. | Paul | 1626,1617 | Done
Done | #bugfix #ui change wind resource file chooser in UI script so it only displays .srw files. Was displaying all weather file extensions even though non-srw files cause wind model simulations to fail. | Paul | 1624 | Done
Done | #ui Update autographs: PV show monthly energy instead of net dc/ac so graph consistent with annual output and shows effect of loss factors, RESCOM net metering graph move legend to bottom and make bars thicker for better readability. | Paul | 1620 | maybe
Done | #ui fix linear fresnel storage page to disable both min/max operating fluid temp for custom fluid | Paul | 1619 | maybe
Done | #ui add empirical trough custom storage HTF option to make it possible to model direct storage with a custom field HTF | Paul | 1640 | maybe
Done | Fix remaining bug with Wind CSM | Janine |  | Done
Done | CEC module library update | Aron |  | Done | Checked in 2015.1.30 branch SAMnt svn rev 1653
Done | Inverter update | Steve |  | Done | Updated through March 2015 in trunk SAMnt rev 1698 and 2015.1.30 branch SAMnt rev 1699
Done | Inverter sizing macro bug fixes | Janine |  | Done